## Unit Testing Defect Template
Type | Defect Category | Project Owner | Team | Subsystem | Module | Owned By | Environment Found In | Found In | Planned For | Priority | Severity | Summary | Description | Labels | Application Defect? | Assigned to | Analysis comments
Defect | Unit Testing | IEDSS | Application Team/Front Office | FO-Data Collection | FO-Data Collection - Income | Rollins, Kevin S | DEV_2 | Release 2.9(CR-4) | /Stage 2/Releases/Release 2.9(CR-4) | Medium | Medium | AUT : Regression scenario EarnedIncome failed for test case EarnedIncome | Scenario: EarnedIncome TestCase: EarnedIncome Step no: {EarnedIncome_EarnedIncome=20} Step name: Unhandled Exception while performing action on Object TANF Step description: There was an Unhandled Exception while executing the keyword selectByVisibleText. Exception: java.lang.reflect.InvocationTargetException Screenshot: EarnedIncome_1.png | DES-AUT | Yes | DES | Yet to review the defect
Defect | Unit Testing | IEDSS | Application Team/Front Office | FO-Data Collection | FO-Data Collection - Income | Rollins, Kevin S | DEV_2 | Release 2.9(CR-4) | /Stage 2/Releases/Release 2.9(CR-4) | Medium | Medium | AUT : Regression scenario SanityTesting failed for test case Complex_Medicaid_SanityTest | Scenario: SanityTesting TestCase: Complex_Medicaid_SanityTest Step no: {EarnedIncome_EarnedIncome=1, SanityTesting_Complex_Medicaid_SanityTest=2} Step name: Unhandled Exception while performing action on Object USERNAME_TXT_FIELD Step description: There was an Unhandled Exception while executing the keyword enter_text. Exception: java.lang.reflect.InvocationTargetException Screenshot: Complex_Medicaid_SanityTest_1.png | DES-AUT | Yes | DES | Yet to review the defect
Defect | Unit Testing | IEDSS | Application Team/Front Office | FO-Data Collection | FO-Data Collection - Income | Rollins, Kevin S | DEV_2 | Release 2.9(CR-4) | /Stage 2/Releases/Release 2.9(CR-4) | Medium | Medium | AUT : Regression scenario Household failed for test case Household | Scenario: Household TestCase: Household Step no: {EarnedIncome_EarnedIncome=1, SanityTesting_Complex_Medicaid_SanityTest=1, Household_Household=2} Step name: Unhandled Exception while performing action on Object USERNAME_TXT_FIELD Step description: There was an Unhandled Exception while executing the keyword enter_text. Exception: java.lang.reflect.InvocationTargetException Screenshot: Household_1.png | DES-AUT | Yes | DES | Yet to review the defect